## Slide 1: Estimation Plan
Orange Computers

## Slide 2
Overview
Small PC manufacturing company
Existing system to record sales and Profits

## Slide 3
New system requirements
Develop a new sales and profit record system:
To handle product line of 40 different products
To accommodate 200 sales people
To accommodate sales data of 30K customers
Be accessible by 11 warehouse clerks
Features : monthly reports

## Slide 4
System should be running on IBM mainframe.
A quicker response time for the sales and profit system.

## Slide 5
Deliverables
An operational Orange computer sales system by Dec 1st 2016.

## Slide 6
Work-Packages
Staffing
Design
Provisioning Hardware/ services
Development/Build of sales software Testing of sales software
Deployment
Reporting
Maintenance and support

## Slide 7
Milestone
Fully staffed by Nov 15th 2015.
Design completion by Feb 28th 2016.
Provisioning of HW done by April 30th 2016.
Development/Build of sales software by July 30th 2016
Testing of sales software done by Sept 20th 2016.
Deployment : by Oct 30th 2016
Reporting : Nov 25th 2016.

## Slide 8
Estimation of scope
Staffing
Development team : 10 developers and 1 lead
QA testing : 3
Design : 4 Operation engineers with knowledge on IBM mainframe, networking, system architecture, deployment and security

## Slide 9
Hardware
IBM mainframes cloud access ( IBM z system )
New IBM PCs for new hires
Software
Security compliance software

## Slide 10
Estimate of Cost
Staffing
5 developers + 4 operational engineers fully burdened cost @ $250,000 per full time employee.
5 contractors @ $100/hr.
3. Full time lead developer @ $300,000 ( fully burdened cost)
3 QA testers @ $200,000 per full time employee ( fully burdened )
Project Manager @ $250,000 fully burdened

## Slide 11
Hardware cost
Mainframe cost @ $800,000
20 IBM PCs @ $2000/ item

## Slide 12
Estimate of Schedule
Work package | Role | Work Effort | Cost
Design | Lead developer + system architect + Operational engineer +project manager | 12 weeks | $233,500
HW Provisioning | Operational engineer + system architect + project manager | 8 weeks | $126,000
Development | Lead developer+ 10 developer + project manager + system architect | 12 weeks | $678,000
Testing | 3 testers + project manager | 8 weeks | $ 142,000

## Slide 13
Work package | Role | Work effort | Cost
Deployment | 2 operational engineers +1 lead developer + project manager | 4 weeks | $88,000
Reporting | 2 developers + Project manager | 4 weeks | $53,000
Operational support ( to be reviewed ) | 1 developer+ 1 operational engineer | 6 months | $ 250,000
Executive Meetings | Project Manager+VP of R&D | 64 months | $39,700
Total projected cost : $2.45MM